## Slide 1
People & Learning
Overview for the Audit Team
September 2026

## Slide 2
Executive Summary
Status of key learning & development programmes and Great Place To Work® 2026 certification
SparX
Fresher talent transformation
2,520
training man-hours delivered
Batch 2 completed 1 Sep 2026 (23-day programme)
16 participants, incl. 11 fresher trainees
Hands-on lab, VR and core skills training
Managerial Excellence
Leadership programme
20
leaders (M4 and above) enrolled
6 of 11 milestones completed; closure planned Jan 2027
Average session rating of 4.5 / 5
Modules span self, people and performance leadership
LearnX LMS
Digital learning platform
500+
employees have used LearnX
Launched 26 Aug 2026 (Enzene India & Inc.)
Leadership, communication, digital & AI and technical courses
Refreshed interface rolling out in Oct
Great Place To Work®
2026 certification
96%
survey response rate (84% in 2025)
Certification retained (Jan 2026 – Jan 2027)
586 of 611 employees took part in the 2026 survey
Survey run by Great Place To Work® Institute, India
Next steps
Oct 2026 – Jan 2027
01
Set up a Buffer Preparation Lab in the Learning Academy
02
Deliver the “Winning Together” MEP module on 9 Oct 2026
03
Run SparX impact reviews: 30-day (Batch 2) and 60-day (Batch 1)
04
Expand the LearnX video library with technical and behavioural courses
Source: Learning Data – Monthly Closing Deck (Sep 2026); Great Place To Work® 2026 survey report

## Slide 3
Learning & Development Programmes
Programme scope, progress to date and digital learning reach (as of September 2026)
SparX
Fresher talent transformation system
2,520
man-hours
23
training days
16
participants
Batch 2 completed on 1 Sep 2026
Focus areas: Manufacturing, Quality and Bio Process Development
Department overviews plus hands-on lab training in pipetting and gowning
VR-based training and core skills, incl. buffer preparation theory
Programme design: boot camp, 12-month rotation, soft skills, competency measurement and 30/60/90-day follow-up
Managerial Excellence Program
20 leaders, M4 and above
6 of 11
milestones completed · avg. session rating 4.5 / 5
Programme study & design
Oct 2025
Self-Leadership
Nov 2025
Refresher session
Aug 2026
Executive Presence
Aug 2026
Developing High Performers
Sep 2026
Cohort Coaching 1
Sep 2026
Winning Together
9 Oct 2026
Influencing without Authority
24 Nov 2026
Conflict Management
9 Dec 2026
Cohort Coaching 2
4 Jan 2027
Final review & closure
28 Jan 2027
LearnX LMS
Launched 26 Aug 2026
500+
employees have used LearnX (Enzene India & Inc.)
Content library
Leading Self & Others
Communication & Effectiveness
Digital & AI
Technical Skills
How it is used
SparX pre-work and refreshers
Role-based learning paths
Completion reports and leaderboard
Refreshed interface from Oct 2026
Source: Learning Data – Monthly Closing Deck (Sep 2026)

## Slide 4
Great Place To Work® 2026
Certification retained for 2026, with a marked rise in employee survey participation
Certification valid
Jan 2026 – Jan 2027
96%
survey response rate in 2026
+12 pts
increase in participation vs 2025
611
employees invited to the survey
Survey participation
Trust Index© survey, Study 2025 vs Study 2026
2025
84% (514 of 610 employees)
2026
96% (586 of 611 employees)
What the survey measures
Five Trust Index© dimensions
Credibility
Respect
Fairness
Pride
Camaraderie
Source: Great Place To Work® Institute, India – 2026 survey report

## Slide 5
Dandiya Night 2025
Colleagues came together to celebrate Navratri with music, dance and festive colour
Life at Enzene
Photos: Enzene Celebrations – Dandiya Night 2025

## Slide 6
Potluck & Reflections 2025
Teams set up food stalls, shared home-cooked dishes and celebrated together
Life at Enzene
Photos: Enzene Celebrations – Potluck and Reflections 2025

## Slide 7
Annual Awards Night 2026
Recognising outstanding contributions at the Annual Awards Night & Talent Show, 31 July 2026
Life at Enzene
Photos: Enzene Annual Awards Night & Talent Show 2026

## Slide 8
Thank you
Passion. Innovation. Life.
For more information visit www.enzene.com